## SEMESTER PROJECT MAIN
Task | Time | Week 1 (1-6 Feb) | [47 empty] | Week 2 (8-13 Feb) | [47 empty] | Week 3 (15-20 Feb) | [47 empty] | Week 4 (22-27 Feb)
|  | Monday | [7 empty] | Tuesday | [7 empty] | Wednesday | [7 empty] | Thursday | [7 empty] | Friday | [7 empty] | Saturday | [7 empty] | Monday | [7 empty] | Tuesday | [7 empty] | Wednesday | [7 empty] | Thursday | [7 empty] | Friday | [7 empty] | Saturday | [7 empty] | Monday | [7 empty] | Tuesday | [7 empty] | Wednesday | [7 empty] | Thursday | [7 empty] | Friday | [7 empty] | Saturday | [7 empty] | Monday | [7 empty] | Tuesday | [7 empty] | Wednesday | [7 empty] | Thursday | [7 empty] | Friday | [7 empty] | Saturday
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
PLANNING | 2 days | Monday 1: PLANNING
Edit Gantt chart | 4 hours | [192 empty] | To do (.) | bar: Monday 1 to Monday 5; Monday 1 to Monday 8; Friday 1 to Friday 8; Monday 1 to Monday 8; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
Research | 7 hours | [192 empty] | Doing (d) | bar: Monday 6 to Tuesday 4; Monday 1 to Monday 8; Friday 1 to Friday 8; Monday 1 to Monday 8; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
Site structure | 4 hours | [192 empty] | Finished (f) | bar: Tuesday 5 to Tuesday 8; Monday 1 to Monday 8; Friday 1 to Friday 8; Monday 1 to Monday 8; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
DESIGNING | 4 days | Wednesday 1: DESIGNING
Branding | 8 hours | bar: Wednesday 1 to Wednesday 8; Monday 1 to Monday 8; Friday 1 to Friday 8; Monday 1 to Monday 8; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
Create style tile | 24 hours | bar: Thursday 1 to Monday 8; Friday 1 to Friday 8; Monday 1 to Monday 8; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
PROTOTYPING | 5 days | Monday 1: PROTOTYPING
Wireframe mobile | 4 hours | bar: Monday 1 to Monday 4; Monday 1 to Monday 8; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
Wireframe desktop | 4 hours | bar: Monday 5 to Monday 8; Monday 1 to Monday 8; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
Prototype on XD | 32 hours | bar: Tuesday 1 to Friday 8; Monday 1 to Monday 8; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
User test | 1 hour | bar: Friday 8; Monday 1 to Monday 8; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
CODING | 10 days | Saturday 1: CODING
Add content HTML | 24 hours | bar: Saturday 1 to Tuesday 8
Check SEO | 4 hours | bar: Wednesday 1 to Wednesday 4
Check HTML | 4 hours | bar: Wednesday 5 to Wednesday 8
Style pages CSS | 48 hours | bar: Thursday 1 to Wednesday 8
FINISHING/REPORT | 1 day | Thursday 1: FINISHING/REPORT
Get user to test | 1 hour | bar: Monday 1 to Monday 8; Thursday 1
Final edits | 9 hours | bar: Monday 1 to Monday 8; Thursday 2 to Friday 2
Report and hand in | 1 day | bar: Monday 1 to Monday 8; Friday 3 to Saturday 8
FLOATING TASKS | 2 days | bar: Monday 1 to Saturday 8; Tuesday 1 to Tuesday 8; Thursday 1 to Thursday 8; Saturday 1 to Saturday 8; Tuesday 1 to Tuesday 8; Thursday 1 to Thursday 8; Saturday 1 to Saturday 8
WCAG colours | 2 hours | bar: Friday 7 to Friday 8
WCAG HTML | 2 hours | bar: Tuesday 4
Write report | 2 days | bar: Thursday 1 to Friday 8
TOTAL: | 24 Days
Note on A5: Adjust the smaller specific Gantts with the new information from the brief
Note on A6: competition and like websites/ target audience
Note on A7: Decide pages and site set up 
Note on A9: Find images, make logo.
Note on A19: make sure it is semantic and neat
Note on A20: Mobile first Responsive Clear and DRY
Note on A24: Includes planning covers why decisions were made how the process was to create the site Link live version of site - online text link prototype - online text Zip file of whole project Report - pdf with correct naming conventions
Note on GG24: Use this time to finish up anything outstanding.
Note on A25: To be completed throughout the project but must be completed within the finished timeframe.
Note on A28: Discuss design and technical aspects of the project. How guidelines for WCAG and SEO and Cintent management were handled

## PLANNING
Task | Time | 1-2 Feb
|  | Monday | [15 empty] | Tuesday
|  | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8 | 0.5 | 1 | 1.5 | 2 | 2.5 | 3 | 3.5 | 4 | 4.5 | 5 | 5.5 | 6 | 6.5 | 7 | 7.5 | 8
EDIT GANTT CHART | 4 hours | EDIT GANT CHART
Read brief | 30 mins | f | [31 empty] | To do (.)
Update individual Gantts | 3 hours |  | f | f | f | f | f | f | [25 empty] | Doing (d)
Update main Gantt | 30 mins | [7 empty] | f | [24 empty] | Finished (f)
RESEARCH | 7 hours | [8 empty] | RESEARCH
Scout the competition | 4 hours | [8 empty] | f | f | f | f | f | f | f | f
Target audience | 3 hours | [16 empty] | f | f | f | f | f | f
SITE STRUCTURE | 4 hours | [22 empty] | SITE STRUCTURE
Pages needed | 2 hours | [22 empty] | f | f | f | f
Site set up | 2 hours | [26 empty] | f | f | f | f
FLOATING TASKS
Write notes for report throughout | [13 empty] | f
TOTAL: | 15 hours
Note on A6: Edit as necessary

## DESIGNING
Task | Time | 3-6 Feb
|  | Wednesday | [7 empty] | Thursday | [7 empty] | Friday | [7 empty] | Saturday
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
BRANDING | 17 hours | Wednesday 1: BRANDING
Graphic Elements | 8 hours | [32 empty] | To do (.) | bar: Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
Colour scheme | 1 hour | [32 empty] | Doing (d) | bar: Wednesday 6 to Thursday 1; Friday 1 to Friday 8
Logo | 8 hours | [32 empty] | Finished (f) | bar: Wednesday 6 to Wednesday 8; Thursday 2 to Friday 8
CREATE STYLE TILE | 10 hours | Friday 2: CREATE STYLE TILE
Typography | 2 hours | bar: Wednesday 1 to Wednesday 8; Friday 2 to Friday 3
Hyperlinks | 1 hour | bar: Wednesday 1 to Wednesday 8; Friday 4
Brand Adjectives | 1 hour | bar: Wednesday 1 to Wednesday 8; Friday 5
Icons & buttons | 2 hours | bar: Wednesday 1 to Wednesday 8; Friday 6 to Friday 7
Arange style tile neatly | 4 hours | bar: Wednesday 1 to Wednesday 8; Friday 8 to Saturday 3
FLOATING TASKS
Check colours WCAG | bar: Wednesday 1 to Wednesday 8; Thursday 6; Friday 1 to Friday 8
Write notes for report throughout | bar: Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
TOTAL: | 27 hours
Note on A5: Make sure these elements will appeal to the target audience and illustrate the purpose of the site. Illustrations and images. images below 200kb
Note on A6: Find colour schemes based on photos and graphic elements to ensure a feeling of conectedness to the website
Note on A7: Simple and attractive to the target audience.
Note on A15: Colours have good contrast text is easy to read

## PROTOTYPING
Task | Time | 8-12 Feb
|  | Monday | [7 empty] | Tueday | [7 empty] | Wednesday | [7 empty] | Thursday | [7 empty] | Friday
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
MOBILE WIREFRAMES | 4 hours | Monday 1: MOBILE WIREFRAMES
Set out screens | 1 hour | [40 empty] | To do (.) | bar: Monday 1
Display content | 2 hours | [40 empty] | Doing (d) | bar: Monday 2 to Monday 3; Wednesday 6 to Wednesday 8; Friday 6 to Friday 8
Check flow with user | 1 hour | [40 empty] | Finished (f) | bar: Monday 4; Wednesday 6 to Wednesday 8; Friday 6 to Friday 8
DESKTOP WIREFRAMES | 4 hours | Monday 5: DESKTOP WIREFRAMES
Set out screens | 1 hour | bar: Monday 1 to Monday 5
Display content | 2 hours | bar: Monday 1 to Monday 7
Check flow with user | 1 hour | bar: Monday 1 to Monday 5; Monday 8
PROTOTYPE ON XD | 32 hours | Tueday 1: PROTOTYPE ON XD
Setup artboards | 1 hour | bar: Monday 1 to Monday 5; Tueday 1; Friday 1 to Friday 8
Design home page | 5 hours | bar: Monday 1 to Monday 5; Tueday 2 to Tueday 6; Friday 1 to Friday 8
Design explore page | 5 hours | bar: Monday 1 to Monday 5; Tueday 7 to Wednesday 8; Friday 1 to Friday 8
Design exhibitions page | 5 hours | bar: Monday 1 to Monday 5; Wednesday 1 to Wednesday 8; Friday 1 to Friday 8
Design special events page | 5 hours | bar: Monday 1 to Monday 5; Thursday 1 to Thursday 5; Friday 1 to Friday 8
Design visit page | 5 hours | bar: Monday 1 to Monday 5; Thursday 6 to Friday 8
Design get involved page | 5 hours | bar: Monday 1 to Monday 5; Friday 1 to Friday 8
User test prototype | 1 hour | bar: Monday 1 to Monday 5; Friday 1 to Friday 8
FLOATING TASKS
Write notes for report throughout | bar: Monday 1 to Monday 5; Tueday 5; Friday 1 to Friday 8
TOTAL: | 40 hours
Note on A4: Low fidelity paper prototype
Note on A7: Using what I learnt from the user I will adjust the flow accordingly site is easy to navigate
Note on A8: Low fidelity paper prototype
Note on A9: Site looks good Class navigation show what page user is on
Note on A10: Text lines are kept short
Note on A11: Using what I learnt from the user I will adjust the flow accordingly

## CODING
Task | Time | 13-24 Feb
|  | Saturday | [7 empty] | Monday | [7 empty] | Tuesday | [7 empty] | Wednesday | [7 empty] | Thursday | [7 empty] | Friday | [7 empty] | Saturday | [7 empty] | Monday | [7 empty] | Tuesday | [7 empty] | Wednesday
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
ADD HTML CONTENT | 24 hours | Saturday 1: ADD HTML CONTENT
Set up GitHub & Netifly | 1 hour | [80 empty] | To do (.) | bar: Saturday 1
Create all files | 1 hour | [80 empty] | Doing (d) | bar: Saturday 2; Tuesday 6 to Tuesday 8
Home page | 3 hours | [80 empty] | Finished (f) | bar: Saturday 3 to Saturday 5; Tuesday 6 to Tuesday 8
Explore page | 3 hours | bar: Saturday 6 to Saturday 8; Tuesday 6 to Tuesday 8
Exhibitions page | 4 hours | bar: Monday 1 to Monday 4; Tuesday 6 to Tuesday 8
Events page | 4 hours | bar: Monday 5 to Monday 8; Tuesday 6 to Tuesday 8
Visit page | 4 hours | bar: Tuesday 1 to Tuesday 4; Tuesday 6 to Tuesday 8
Get involved page | 4 hours | bar: Tuesday 5 to Tuesday 8
CHECK SEO | 4 hours | Wednesday 1: CHECK SEO
Unique meta & title | 2 hours | bar: Saturday 1 to Saturday 5; Wednesday 1 to Wednesday 2
Heading order | 1 hour | bar: Saturday 1 to Saturday 5; Wednesday 3
No images for words | 1 hour | bar: Saturday 1 to Saturday 5; Wednesday 4
CHECK HTML | 4 hours | Wednesday 5: CHECK HTML
Semantic elements | 2 hours | bar: Saturday 1 to Saturday 5; Wednesday 5 to Wednesday 6; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5
Neat nesting | 1 hour | bar: Saturday 1 to Saturday 5; Wednesday 7; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5
Logical order | 1 hour | bar: Saturday 1 to Saturday 5; Wednesday 8 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5
STYLE PAGES CSS | 48 hours | Thursday 1: STYLE PAGES CSS
Home page | 7 hours | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 7; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5
Explore page | 7 hours | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Thursday 8 to Friday 6; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5
Exhibitions page | 7 hours | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Friday 7 to Saturday 5; Tuesday 1 to Tuesday 5
Events page | 7 hours | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Saturday 1 to Monday 4; Tuesday 1 to Tuesday 5
Visit page | 7 hours | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Monday 5 to Tuesday 5
Get involved page | 9 hours | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Wednesday 4
Check responsive | 2 hours | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5; Wednesday 5 to Wednesday 6
Check DRY | 1 hour | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5; Wednesday 7
Check neat nesting | 1 hour | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5; Wednesday 8
FLOATING TASKS
Check HTML WCAG | bar: Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 8; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5
Write notes for report throughout | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 6
publish on netifly | bar: Saturday 1 to Saturday 5; Thursday 1 to Thursday 5; Saturday 1 to Saturday 5; Tuesday 1 to Tuesday 5; Wednesday 8
TOTAL: | 80 hours
Note on A5: GitHub repository should be set to private
Note on A17: make sure it is semantic and neat Meta Viewport in head of document unique title one unique h1 unique meta description
Note on A21: Mobile first Responsive Clear and DRY
Note on A28: Looks good on all screen sizes.
Note on A29: Don't repeat styles in media queries
Note on A32: Alt text for images No images for text Semantic elements where possible Logical order for screen readers heading order